## Synthèse
Activité | Total | BETA | MVP | Event
Développement | 406.05 | 214 | 151.9 | 40.2
Infra As Code | 20 | 20
Tests d'integration | 40.605 | 21.4 | 15.19 | 4.02
Documentation | 8.121 | 4.28 | 3.038 | 0.804
MEP and Hypercare | 12.1815 |  | 11 | 1.206
Pilotage | 58.4349 | 31.1616 | 21.7354 | 5.5476
Total | 545.3924 | 290.8416 | 202.8634 | 51.7776
TJM HT | 1632.99
Prix HT | 806215.2626 | 474941.4244 | 331273.8382 | Offerte
Estimation TMA
Activité | Total
TMA | 78
SysOps | 52
Pilotage | 15.6
Total | 145.6
TJM HT | 1632.99
Prix HT | 237763.344

## Spécifications Chiffrage Dét.
Catégorie | Écran/Composant | Version | Type | Fonctionnalité | Boutons/Actions | Flow Utilisateur | Endpoints Backend (FastAPI) | Microservice | Collections PostgreSQL | Champs Principaux | Estimation FE (j) | Estimation BE (j) | Estimation DB (j) | Estimation Totale | Complexité | Notes Techniques
ONBOARDING | Splash Screen | Beta | Écran | Animation démarrage - Carte Casablanca → Logo LYFE → Signe paix | Aucun bouton interactif | Ouverture app → Animation 3sec → Redirection auto vers Auth | GET /api/config/splash GET /api/assets/animation | Assets Service | app_config | animation_url, version, duration_ms | 0.1 | 0.2 | 0.1 | 0.4 | Simple | Animation Lottie/JSON, preload assets
AUTHENTICATION | Login/Signup | Beta | Écran | Système authentification complet avec biométrie et consentements | Connexion par Email/Password Face ID Connexion Sociale (Google/Facebook/Apple) Se souvenir de moi Continuer en invité S'inscrire Mot de passe oublié | Landing → Choix auth → Email/Social/Guest → Consentements → Vérification → Dashboard Flow invité: accès limité (lecture seule, pas de booking) | POST /api/auth/register {email, password, consents} POST /api/auth/login {email, password} POST /api/auth/social {provider, token} POST /api/auth/biometric {device_id, biometric_token} POST /api/auth/guest → session temporaire POST /api/auth/verify-email {token} POST /api/auth/forgot-password {email} GET /api/auth/me | Auth Service | users, user_sessions, user_consents, user_devices | email, password_hash, phone, full_name, date_of_birth, location, marketing_consent, data_consent, location_consent, biometric_enabled, social_provider, device_fingerprint, email_verified, created_at | 0.2 | 4 | 1 | 5.2 | Moyen | OAuth2 + JWT, Argon2 password hashing, rate limiting, 2FA optional, GDPR compliance
| Consentements | Beta | Fonctionnalité cachée | Collecte permissions marketing et données | Accepter tout Personnaliser Cases individuelles: Marketing, Localisation, Données comportementales, Notifications Push | Inscription → Modal consentements → Détails pourquoi important → Validation → Compte créé | POST /api/users/{id}/consents {consents_array} GET /api/legal/privacy-policy GET /api/legal/terms | Auth Service | user_consents | user_id, consent_type, granted, timestamp, ip_address, version | 0.1 | 2 | 0.5 | 2.6 | Simple | GDPR/CCPA compliant, versioning des consentements, audit trail
NAVIGATION | Menu Principal | Beta | Écran | Hub navigation 3 catégories | Restaurants Drinks Events Logo LYFE (retour home) | Dashboard → Sélection catégorie → Feed filtré par catégorie Navigation persistante en footer | GET /api/categories | Content Service | categories | name, icon, description, order, active | 0.1 | 0.3 | 0.2 | 0.6 | Simple | Deep linking vers chaque catégorie
| Bottom Navigation | Beta | Layout | Barre navigation principale | Feed Search + (Action rapide) My Bookings Profile | Accessible depuis tous les écrans principaux + ouvre quick actions: Nouvelle réservation, Partager lieu, Ajouter photo | Aucun endpoint dédié | N/A | N/A | N/A | 0.1 | 0 | 0 | 0.1 | Simple | Tab navigation React Native, badge notifications sur Bookings
FEED | Feed Principal | Beta | Écran | Hub social avec posts utilisateurs et recommandations | Pull to refresh Like/Unlike post Commenter Partager Sauvegarder lieu Voir profil auteur Filtres (Distance, Note, Prix, Cuisine) Segmented control: Feed / Your List / Leaderboard | Home → Feed chargé → Scroll infini → Engagement (like/comment/share) → Détail lieu Analytics: Tous les clics, scrolls, temps passé par post | GET /api/feed?user_id=&page=&filters= POST /api/feed/posts GET /api/feed/posts/{id} POST /api/posts/{id}/like DELETE /api/posts/{id}/like POST /api/posts/{id}/comment {text} GET /api/posts/{id}/comments POST /api/posts/{id}/share | Social Service | posts, post_likes, post_comments, post_shares, user_feed_views | post_id, user_id, venue_id, content, media_urls, likes_count, comments_count, shares_count, timestamp, location_lat, location_lng | 0.2 | 4 | 1 | 5.2 | Moyen | Algorithme de ranking feed (engagement + recency + preferences), infinite scroll, image compression, CDN pour media
| Stories Carousel | MVP | Composant | Stories 24h type Instagram/Snapchat | Voir story Créer story (+ bouton) Story suivante (tap droite) Story précédente (tap gauche) Fermer Partager story | Feed → Carousel stories en haut → Tap story → Fullscreen viewer → Swipe stories → Expire 24h | GET /api/stories?active=true POST /api/stories {media, venue_id, duration} GET /api/stories/{id} POST /api/stories/{id}/view DELETE /api/stories/{id} | Social Service | stories | story_id, user_id, venue_id, media_url, created_at, expires_at, views_count, story_type | 0.15 | 3.5 | 1 | 4.65 | Moyen | Compression video/image, expiration automatique, analytics de vues
| Post Creation | MVP | Fonctionnalité | Créer nouveau post avec photo/vidéo | Choisir photo/vidéo Tag lieu (autocomplete) Ajouter texte/émojis Publier Sauvegarder brouillon | + Button → Modal création → Upload media → Tag venue → Caption → Publish Compression avant upload | POST /api/posts {media, venue_id, content, location} GET /api/venues/search?q= (autocomplete tag) POST /api/media/upload | Social Service | posts | user_id, venue_id, content, media_urls, location, created_at | 1.5 | 2.5 | 0.5 | 4.5 | Moyen | Media upload S3/CloudFlare, compression client-side, moderation queue
DISCOVERY | Restaurants List | Beta | Écran | Listing restaurants avec filtres avancés | Voir détail restaurant Filtrer (Cuisine, Prix, Distance, Note, Ouvert maintenant) Trier (Pertinence, Distance, Note, Prix) Sauvegarder favori Partager Réserver (quick action) | Restaurants tab → Liste avec cards → Filtres → Tri → Tap card → Détail restaurant Analytics: Filtres utilisés, tris, clics, scroll depth | GET /api/venues/restaurants?city=&cuisine=&price=&rating=&distance=&open_now=&sort=&page= GET /api/venues/restaurants/{id} POST /api/users/{id}/favorites {venue_id} DELETE /api/users/{id}/favorites/{venue_id} | Venue Service | restaurants, restaurant_cuisines, restaurant_amenities, user_favorites | venue_id, name, cuisine_type, price_level, rating, location, phone, website, opening_hours, capacity, images, description | 0.2 | 2 | 0.5 | 2.7 | Simple | Elasticsearch pour recherche full-text, PostGIS pour geo-queries, Redis cache, index composites
| Drinks/Bars List | Beta | Écran | Listing bars et lounges avec catégories | Filtrer par type: Bar, Rooftop, Wine Bar, Cocktail Lounge Voir détail bar Réserver table Sauvegarder Voir happy hours Partager | Drinks tab → Catégories → Liste bars → Filtres → Détail Analytics identiques restaurants | GET /api/venues/drinks?type=&city=&filters= GET /api/venues/drinks/{id} GET /api/venues/{id}/happy-hours | Venue Service | drinks_venues | venue_id, bar_type, specialties, happy_hour_times, ambiance_tags, dress_code, music_genre | 0.2 | 1.5 | 0.5 | 2.2 | Simple | Même infra que restaurants, filtres spécifiques drinks
| Events List | Event | Écran | Listing événements avec billetterie | Filtrer: Concerts, Festivals, Nightlife, Culture, Sports, Workshops Acheter billets RSVP gratuit Intéressé (remind me) Partager événement Voir capacité restante | Events tab → Liste → Filtres date/type → Tap event → Détail → Ticket selection → Checkout Analytics: Clics tickets, abandons panier, conversions | GET /api/events?type=&date_from=&date_to=&city=&price_min=&price_max= GET /api/events/{id} POST /api/events/{id}/interested POST /api/events/{id}/rsvp GET /api/events/{id}/tickets POST /api/tickets/reserve {event_id, quantity, ticket_type} | Events Service | events, event_tickets, event_categories, event_rsvps, ticket_inventory | event_id, title, description, venue_id, date_time, capacity, tickets_available, price, category, images, organizer_id | 0.2 | 4 | 1 | 5.2 | Moyen | Inventory management temps réel, race condition handling, webhook intégration paiement
BOOKING | Booking Flow Restaurant | Beta | Flow | Réservation restaurant/Drink multi-étapes | Sélectionner nombre invités (+/-) Choisir date (calendrier) Choisir heure (slots disponibles) Demandes spéciales (textarea) Code promo Confirmer réservation Annuler | Détail restaurant → Réserver → Step 1: Invités → Step 2: Date → Step 3: Heure → Step 4: Spécial requests → Step 5: Confirmation Validation disponibilité à chaque step | POST /api/bookings/check-availability {venue_id, date, time, guests} POST /api/bookings {venue_id, date, time, guests, special_requests, promo_code} GET /api/bookings/{id} PUT /api/bookings/{id} (modifier) PUT /api/bookings/{id}/cancel POST /api/bookings/{id}/confirm | Booking Service | bookings, booking_slots, venue_availability, promo_codes | booking_id, user_id, venue_id, booking_date, booking_time, guests_count, special_requests, status, booking_reference, qr_code, promo_code, points_earned, created_at | 0.2 | 5 | 1.5 | 6.7 | Moyen | Stepper UI, validation temps réel disponibilité, génération QR code, push notifications confirmation, rate limiting anti-spam
| Booking Flow Event | Event | Flow | Achat billets événement avec sélection type/quantité | Sélectionner type billet (VIP, Standard, Early Bird) Quantité par type (+/-) Voir prix total Code promo Conditions générales (checkbox) Payer / Réserver | Détail event → Get Tickets → Sélection type/qty → Récap prix → Paiement → Confirmation Lock temporaire tickets (10min) pendant checkout | POST /api/events/{id}/tickets/lock {ticket_types, quantities} POST /api/bookings/event {event_id, tickets, payment_method, promo_code} POST /api/payments/process (Stripe/Mollie) POST /api/payments/webhook GET /api/bookings/event/{id} | Booking Service + Payment Service | event_bookings, event_tickets_purchased, ticket_locks, payments | booking_id, event_id, user_id, tickets_json, total_price, payment_status, payment_id, confirmation_code, qr_codes | 2 | 7 | 2 | 11 | Complexe | Stripe/Mollie SDK, webhook handling, ticket locking (Redis), inventory race conditions, refund logic, email tickets PDF
| Check Availability | MVP | Fonctionnalité cachée | Vérification disponibilité temps réel | Aucun bouton visible Requête auto lors sélection date/heure | Transparent pour utilisateur, requis avant confirmation Cache résultats 30sec pour même slot | GET /api/bookings/availability?venue_id=&date=&time=&guests= Response: {available: boolean, alternative_slots: []} | Booking Service | venue_availability | venue_id, date, time_slot, capacity, booked_count, available_count | 0 | 2 | 0.5 | 2.5 | Simple | Redis cache, algorithme matching alternatives, considérer no-shows historiques
0
MY BOOKINGS | Bookings List | Beta | Écran | Liste réservations active/passées | Onglets: Active / Past Filtrer par: Restaurant/Event/Drinks, Statut, Date Voir détail réservation Modifier réservation Annuler réservation Directions Appeler venue Partager booking Ajouter au calendrier Noter maintenant (si past) | My Bookings tab → Liste segmentée → Tap booking → Détail → Actions contextuelles Push notification 2h avant: Rappel + directions | GET /api/bookings?user_id=&status=&type=&page= GET /api/bookings/{id} PUT /api/bookings/{id}/modify PUT /api/bookings/{id}/cancel POST /api/bookings/{id}/share | Booking Service | bookings | booking_id, user_id, venue_id, event_id, status, booking_reference, qr_code, date_time, guests, special_requests, rating_submitted, created_at, updated_at | 0.2 | 2 | 0.5 | 2.7 | Simple | Calendar integration (iCal), deep links directions, QR code display, status sync temps réel
| Booking Confirmation | Beta | Écran | Écran confirmation post-booking | Terminé / Partager Ajouter au calendrier Voir QR code (fullscreen) Télécharger reçu/billet Directions | Après confirmation booking → Écran success → Points gagnés affiché → Actions Email/SMS confirmation automatique | GET /api/bookings/{id}/confirmation GET /api/bookings/{id}/qr-code GET /api/bookings/{id}/receipt.pdf POST /api/bookings/{id}/send-confirmation {method: email/sms} | Booking Service + Notification Service | bookings | booking_reference, qr_code, receipt_url, calendar_link | 0.5 | 1.5 | 0.3 | 2.3 | Simple | Génération PDF, envoi email async (queue), deep link calendar
RATING | Rating Flow | Beta | Flow | Notation restaurant après visite | Sentiment rapide: 😊 J'ai aimé / 😐 C'était correct / 😞 Je n'ai pas aimé Comparables: Meilleur/Pire/Identique vs 3 autres Catégories détaillées: Service, Hygiène, Ambiance, Nourriture, Rapport qualité-prix (1-5⭐) Commentaire (optionnel) Photos (optionnel) Publier / Passer | Push 1-2h après créneau → Modal rating → Step 1: Sentiment → Step 2: Comparables → Step 3: Détails optionnels → Publication Formule: Score = Base (😊=9, 😐=6.5, 😞=4) + Ajustements comparables | POST /api/ratings {booking_id, sentiment, comparables, categories, comment, photos} GET /api/venues/{id}/comparable-venues PUT /api/bookings/{id}/rating-submitted GET /api/ratings/{id} PUT /api/venues/{id}/aggregate-rating | Rating Service | venue_ratings, rating_comparables, rating_categories | rating_id, user_id, venue_id, booking_id, sentiment_score, final_score, service_rating, hygiene_rating, ambiance_rating, food_rating, value_rating, comment, photos, helpful_count, created_at | 1 | 2 | 1 | 4 | Moyen | Algorithme scoring pondéré, ranking comparables (même cuisine + proximité + notes utilisateur), agrégation rating venue (moyenne pondérée), moderation IA commentaires
| Rating Display | Beta | Composant | Affichage ratings sur pages venues | Voir toutes les notes Filtrer par note (5⭐, 4⭐...) Trier: Plus récentes, Plus utiles, Note haute/basse Marquer utile Signaler abus | Page venue → Section reviews → Liste ratings → Filtres/tri → Tap rating → Détail full Analytics: Taux lecture reviews, filtres utilisés | GET /api/venues/{id}/ratings?sort=&filter_rating=&page= POST /api/ratings/{id}/helpful POST /api/ratings/{id}/report {reason} | Rating Service | venue_ratings | rating_id, helpful_count, reported, verified_visit | 2 | 1 | 0.5 | 3.5 | Simple | Badge 'Verified Visit' si rating lié booking, anti-spam helpful, moderation reports
PROFILE | User Profile | Beta | Écran | Profil utilisateur public/privé | Éditer profil Changer photo Suivre / Ne plus suivre Partager profil Onglets: Posts, Reviews, Bookings (si soi-même), Lists Voir badges Voir statistiques: Restaurants visités, Reviews écrites, Followers, Following Paramètres (si soi-même): Confidentialité, Notifications, Déconnexion | Profile tab → Voir profil → Éditer (si soi) / Suivre (si autre) → Onglets contenu Settings: Privacy (Public/Friends/Private), Notif preferences | GET /api/users/{id} PUT /api/users/{id} {name, bio, avatar, location} POST /api/users/{id}/follow DELETE /api/users/{id}/unfollow GET /api/users/{id}/followers GET /api/users/{id}/following GET /api/users/{id}/stats GET /api/users/{id}/posts GET /api/users/{id}/reviews POST /api/media/upload (avatar) | User Service | users, user_follows, user_stats, user_privacy_settings | user_id, name, username, bio, avatar_url, location, restaurants_visited, reviews_count, followers_count, following_count, influence_score, badges, privacy_level, notification_preferences | 0.3 | 3 | 1 | 4.3 | Moyen | Image upload S3, username unique validation, influence score algo (engagement + reach), badge system, privacy controls granulaires
| Settings | Beta | Écran | Paramètres compte et préférences | Infos personnelles (nom, email, téléphone, date naissance) Confidentialité: Profil Public/Friends/Private, Masquer activité Notifications: Push, Email, SMS (toggle chacune) Préférences culinaires & allergies Langue & région Déconnexion Supprimer compte | Profile → Settings icon → Sections settings → Modifications → Sauvegarder Suppression compte: Modal confirmation + délai 30j | PUT /api/users/{id}/settings {settings_json} PUT /api/users/{id}/preferences {cuisines, allergies} PUT /api/users/{id}/privacy {privacy_settings} POST /api/auth/logout DELETE /api/users/{id}/delete-request | User Service | user_settings | user_id, privacy_settings, notification_preferences, dietary_preferences, language, region | 0.1 | 1.5 | 0.5 | 2.1 | Simple | GDPR right to be forgotten, soft delete avec anonymisation données, email confirmation changements critiques
LOYALTY | Loyalty Program | MVP | Écran | Programme fidélité gamifié | Dashboard points: Total, Ce mois, Lifetime, Expirant Voir niveau actuel (Standard/Gold/Platinum/Diamond) Barre progression niveau suivant Historique transactions Récompenses disponibles Échanger points → Réduction/Coupon Règles du programme | Profile → Loyalty → Dashboard → Échanger points / Voir historique Points gagnés automatiquement après booking confirmé + check-in QR vérifié | GET /api/loyalty/dashboard?user_id= GET /api/loyalty/transactions?user_id= GET /api/loyalty/rewards?user_id= POST /api/loyalty/redeem {reward_id} GET /api/loyalty/tiers | Loyalty Service | loyalty_accounts, loyalty_transactions, loyalty_rewards, loyalty_tiers | account_id, user_id, total_points, current_tier, points_this_month, lifetime_points, expiring_points, tier_multiplier | 0.2 | 2 | 1 | 3.2 | Moyen | Calcul points avec multiplicateurs tiers, expiration points (2 ans), dégradation tier automatique, génération coupons uniques, webhook restaurants pour validation coupons
| Points Earning | MVP | Fonctionnalité cachée | Gagnage points automatique | Aucune action utilisateur Automatique après booking validé | Booking confirmé → User check-in (QR scan ou auto 15min après heure) → Points calculés (base × multiplicateur tier) → Notification '+X points gagnés!' No-show détecté → Aucun point + pénalité potentielle | POST /api/loyalty/award-points {booking_id, user_id} POST /api/bookings/{id}/check-in {qr_code / auto} POST /api/bookings/{id}/no-show | Loyalty Service + Booking Service | loyalty_transactions | transaction_id, user_id, booking_id, points_earned, tier_multiplier, transaction_type, created_at |  | 1 | 0.5 | 1.5 | Simple | QR validation côté restaurant (app partenaire), auto check-in si booking < 15min début, détection no-show (restaurant signale), rollback points si annulation post check-in
LEADERBOARD | Leaderboard | MVP | Écran | Classement communautaire amis | Onglets: Top Explorateurs (par défaut), Notes Contacts Classement amis par: Lieux visités, Reviews écrites, Utilité reviews Voir profil ami Ajouter ami (téléphone/email) Accepter/Refuser demande ami Activité récente amis | Leaderboard tab → Top Explorateurs → Liste amis triée → Tap ami → Profil Demande ami: Search contact → Envoyer → Notification → Accepter/Refuser | GET /api/leaderboard/friends?user_id=&sort=visits¦reviews¦helpful GET /api/users/{id}/friends POST /api/users/{id}/friend-requests {contact} PUT /api/friend-requests/{id}/accept PUT /api/friend-requests/{id}/reject GET /api/users/{id}/activity-feed | Social Service | user_friends, friend_requests, user_activity_feed | friendship_id, user_id, friend_id, status, requested_at, accepted_at, activity_id, activity_type, venue_id, timestamp | 0.2 | 3 | 1 | 4.2 | Moyen | Contact sync permission, ranking algo (tiebreakers multiples), real-time activity feed (WebSocket ou polling), notification système demandes
| Community Posts | Beta (entre nous et amis proche) | Fonctionnalité | Posts communautaires liés classement | Notification: 'Partager expérience avec amis?' 15-30min après début booking Ajouter photo/story/avis rapide Post visible dans feed amis | Post-booking (15-30min) → Push notif → Modal quick post → Photo/caption → Publier → Apparaît feed amis + attaché venue page Analytics: Taux réponse notif, engagement posts | POST /api/community/posts {booking_id, content, media} GET /api/community/feed?user_id= (feed amis) POST /api/posts/{id}/like POST /api/posts/{id}/comment | Social Service | community_posts | post_id, user_id, booking_id, venue_id, content, media_url, created_at, visibility | 0.2 | 2 | 0.5 | 2.7 | Moyen | Timing intelligent notification (pas spam), compression media, visibilité posts (friends-only), lien venue page
LISTS | Saved Places | Beta | Écran | Listes de lieux sauvegardés | Onglets: Saved, Visited, Wishlist Créer liste personnalisée Ajouter lieu à liste Retirer de liste Partager liste Trier: Date ajout, Nom, Note Filtrer: Type (Restaurant/Drink/Event), Ville | Profile → Lists → Onglets → Tap lieu → Détail Créer liste: + → Nom liste → Ajouter lieux → Publique/Privée Analytics: Conversion wishlist→visite, fréquence consultation | GET /api/lists?user_id= POST /api/lists {name, description, public} GET /api/lists/{id}/venues POST /api/lists/{id}/venues {venue_id} DELETE /api/lists/{id}/venues/{venue_id} POST /api/lists/{id}/share | User Service | user_lists | list_id, user_id, name, description, public, created_at, venue_list_items | 1.5 | 2.5 | 0.8 | 4.8 | Moyen | Listes prédéfinies: Saved, Visited (auto), Wishlist, listes custom, partage listes (deeplink + preview), analytics conversion
| Visited History | Beta | Fonctionnalité cachée | Historique visites automatique | Aucune action manuelle Auto-ajouté après check-in booking | Booking check-in validé → Ajout automatique liste 'Visited' → Badge 'Visited' sur venue page pour user Analytics: Fréquence visites, patterns (jour/heure), revisites | POST /api/lists/visited/add {user_id, venue_id, booking_id, visit_date} GET /api/users/{id}/visit-history GET /api/analytics/user-patterns?user_id= | User Service + Analytics Service | user_visit_history | visit_id, user_id, venue_id, booking_id, visit_date, visit_count | 0.1 | 1.5 | 0.5 | 2.1 | Moyen | Auto-tracking visites, analytics patterns (ML), badge visited sur UI, recommendations basées historique
SEARCH | Global Search | Beta | Écran | Recherche unifiée multi-entités | Barre recherche avec suggestions temps réel Filtres: All, Restaurants, Bars, Events, Members Filtres avancés (modal): Prix, Note, Distance, Cuisine, Open Now Trier: Pertinence, Distance, Note, Prix Recherche vocale Recherche par photo (future) | Tap search → Saisie query → Suggestions dropdown → Résultats mixtes → Filtres → Détail Analytics: Tous termes, filtres, clics, abandon, conversion | GET /api/search?q=&type=&filters=&sort=&page= GET /api/search/suggestions?q= (autocomplete) POST /api/search/voice {audio_file} POST /api/analytics/search-event {query, filters, results_count, clicked_result} | Search Service + Analytics Service | search_logs | search_id, user_id, query, filters, results_count, clicked_result_id, location, timestamp | 1 | 4.5 | 1.5 | 7 | Complexe | Elasticsearch full-text search, typo tolerance, synonymes, boost popularité, PostGIS geo-search, voice-to-text, search analytics ML pour améliorer ranking
| Popular Near You | Beta | Fonctionnalité | Recommendations géolocalisées | Section 'Popular near you' en haut résultats Basé sur localisation temps réel Rafraîchir si déplacement significatif | Search → Géoloc détectée → Query top venues rayon 5km → Affiché en premier Analytics: Taux clic popular vs autres résultats | GET /api/search/popular-nearby?lat=&lng=&radius=5000 Cache: Redis 10min par zone géographique | Search Service | N/A (query dynamique) | Cache: zone_hash, top_venues_ids, cached_at | 0.1 | 1.5 | 0.3 | 1.9 | Simple | Geohash pour cache zones, ranking popularité (visites récentes + ratings), refresh si user bouge >1km
| Search Analytics | MVP | Fonctionnalité cachée | Tracking exhaustif recherches | Aucune UI visible Tracking backend toutes interactions | Chaque recherche → Log: query, filtres, résultats, clics, temps, abandon Agrégation: Trending searches, zero-results, conversion rates | POST /api/analytics/search {query, filters, results, clicked, converted, time_spent, location, timestamp} GET /api/analytics/search-trends?period=7d GET /api/analytics/zero-results-queries | Analytics Service | search_analytics | log_id, user_id, query, filters_json, results_count, clicked_result_id, converted, time_spent, location, timestamp | 0 | 2.5 | 1 | 3.5 | Simple | BigQuery ou ClickHouse pour analytics, dashboards internes, ML pour améliorer search, détection opportunités business (queries sans résultats)
SOCIAL | Follow System | MVP | Fonctionnalité | Système abonnements utilisateurs | Suivre / Ne plus suivre Voir followers Voir following Bloquer utilisateur Signaler profil | Profil user → Bouton Follow → Notification destinataire → Acceptation auto (si public) ou manuelle (si privé) Analytics: Graph social, influenceurs, communautés | POST /api/users/{id}/follow DELETE /api/users/{id}/unfollow GET /api/users/{id}/followers?page= GET /api/users/{id}/following?page= POST /api/users/{id}/block POST /api/users/{id}/report {reason} | Social Service | user_follows | follow_id, follower_id, followed_id, created_at, status | 1.5 | 2 | 0.5 | 4 | Moyen | Notification système, privacy (public follow auto, private nécessite approbation), block list, graph social analysis
| Share Functionality | Beta | Fonctionnalité | Partage cross-platform | Partager vers: WhatsApp, Instagram, Facebook, Twitter, SMS, Email, Copier lien Deeplink vers contenu partagé Preview card génération | Bouton Share (venue/post/booking) → Modal partage → Sélection plateforme → Intent natif / deeplink Analytics: Plateforme, contenu partagé, tracking referrals | POST /api/share {content_type, content_id, platform} GET /api/share/preview/{share_id} (Open Graph meta) GET /api/analytics/referrals?share_id= | Social Service + Analytics Service | shares | share_id, user_id, content_type, content_id, platform, referral_code, clicks, conversions, created_at | 1 | 2 | 0.5 | 3.5 | Moyen | Deep linking (Branch.io/Firebase), Open Graph meta generation, referral tracking codes, viral coefficient calculation
NOTIFICATIONS | Push Notifications | Beta (confirmation de reservation, noter le restaurant après la confirmation du restaurateur, + après uen heure du rendez vous ) | Système | Notifications push contextuelles | Aucun bouton UI dédié Settings: Toggle par type notification | Divers déclencheurs → Queue notification → Firebase/APNs → Push delivery → Tap → Deep link Types: Booking reminder (2h avant), Rating request (1-2h après), Friend request, New follower, Post like/comment, Promo/marketing | POST /api/notifications/send {user_id, type, title, body, deep_link} GET /api/notifications?user_id=&page= PUT /api/notifications/{id}/read POST /api/notifications/register-device {device_token, platform} DELETE /api/notifications/unregister-device | Notification Service | notifications | notification_id, user_id, type, title, body, deep_link, read, sent_at, delivered_at, opened_at | 1.5 | 3.5 | 1 | 6 | Moyen | Firebase Cloud Messaging / APNs, device token management, notification queue (Redis/RabbitMQ), delivery tracking, A/B testing notifs, opt-out management
| In-App Notifications | MVP | Composant | Centre notifications in-app | Badge compteur non-lues Liste notifications Marquer lue Marquer toutes lues Supprimer notification Filtrer par type | Bell icon (header) → Badge si non-lues → Tap → Liste notifications → Tap notif → Deep link contenu Refresh temps réel via WebSocket | GET /api/notifications?user_id=&unread=true PUT /api/notifications/{id}/read PUT /api/notifications/mark-all-read DELETE /api/notifications/{id} WebSocket: wss://api/notifications/stream | Notification Service | notifications | notification_id, read, deleted_at | 0 | 2 | 0.5 | 2.5 | Simple | WebSocket pour temps réel, badge update, grouping notifications similaires, expiration auto après 30j
VENUE_DETAILS | Restaurant Detail | Beta | Écran | Page détail restaurant complète | Réserver table Appeler restaurant Voir site web Directions / GPS Partager restaurant Sauvegarder / Favori Voir menu (PDF/images) Galerie photos (fullscreen) Voir horaires (expand/collapse) Équipements / Amenities Lire reviews Écrire review Voir événements associés | Liste restaurants → Tap → Détail chargé → Scroll sections → Actions Analytics: Temps passé, sections vues, clics CTA, scroll depth | GET /api/restaurants/{id} GET /api/restaurants/{id}/menu GET /api/restaurants/{id}/photos GET /api/restaurants/{id}/hours GET /api/restaurants/{id}/amenities GET /api/restaurants/{id}/reviews GET /api/restaurants/{id}/events POST /api/analytics/venue-view {venue_id, sections_viewed, time_spent} | Venue Service | restaurants | venue_id, name, description, cuisine, price_level, phone, website, location, menu_url, photos, hours, amenities, capacity, rating, reviews_count | 0.2 | 2.5 | 1 | 3.7 | Moyen | Image lazy loading, menu PDF viewer, map embed, hours parsing, amenities icons, review pagination
| Drinks Venue Detail | Beta | Écran | Page détail bar/lounge | Réserver table Voir happy hours Appeler bar Voir carte cocktails Directions Partager Sauvegarder Galerie Horaires Ambiance tags (Cozy, Vibrant, Intimate) Musique / Genre Dress code | Similar to restaurant detail Sections spécifiques: Happy hours, Cocktail specialties, Music genre, Dress code Analytics identiques | GET /api/drinks/{id} GET /api/drinks/{id}/happy-hours GET /api/drinks/{id}/cocktail-menu Similar endpoints to restaurants | Venue Service | drinks_venues | venue_id, bar_type, happy_hour_times, specialties, ambiance_tags, music_genre, dress_code | 0.2 | 2 | 0.5 | 2.7 | Moyen | Happy hours affichage temps réel (active/inactive), cocktail menu carousel, ambiance badges
| Event Detail | Event | Écran | Page détail événement | Acheter billets / Get Tickets RSVP (si gratuit) Intéressé (remind me) Partager événement Voir venue associé Directions Ajouter calendrier Voir line-up (si concert) Voir organisateur Voir capacité restante Photos/Vidéos teaser | Liste events → Tap → Détail → Get Tickets → Modal sélection Analytics: Vues, interested clicks, ticket clicks, conversions, abandons | GET /api/events/{id} GET /api/events/{id}/venue GET /api/events/{id}/lineup GET /api/events/{id}/organizer GET /api/events/{id}/tickets/availability POST /api/events/{id}/interested POST /api/events/{id}/rsvp | Events Service | events | event_id, title, description, venue_id, date_time, end_time, capacity, available_tickets, price_range, category, lineup, organizer_id, images, videos | 1 | 2.5 | 1 | 4.5 | Moyen | Video preview autoplay, countdown to event, dynamic capacity indicator, lineup carousel, calendar ICS generation
ADMIN | Restaurant Dashboard | Beta | Écran (Business) | Dashboard restaurant partenaire | Voir réservations du jour Accepter/Refuser réservation Marquer présence (QR scan) Signaler no-show Modifier disponibilités Voir analytics: Taux remplissage, revenue estimé, taux no-show Promouvoir restaurant (boost listing) Répondre reviews | Separate business app/web Login restaurant → Dashboard → Réservations list → Actions Analytics temps réel | GET /api/business/bookings?venue_id=&date= PUT /api/business/bookings/{id}/confirm PUT /api/business/bookings/{id}/reject POST /api/business/bookings/{id}/check-in {qr_code} POST /api/business/bookings/{id}/no-show PUT /api/business/venues/{id}/availability GET /api/business/analytics?venue_id= | Business Service | business_accounts | business_id, venue_id, owner_id, subscription_tier, features_enabled | 4 | 8 | 2 | 14 | Complexe | QR scanner app, analytics dashboards (Chart.js), revenue tracking, subscription tiers (Free/Premium/Enterprise), notification système nouvelles réservations
| Event Organizer Dashboard | Event | Écran (Business) | Dashboard organisateur événements | Créer événement Gérer billets (types, prix, capacité) Voir ventes temps réel Scanner billets (check-in) Voir analytics: Ventes par jour, taux conversion, revenue Export liste participants Envoyer annonces participants Rembourser billets | Business web portal Create event → Setup tickets → Publish → Monitor sales → Check-in day-of Email confirmations auto | POST /api/business/events {event_details} PUT /api/business/events/{id} POST /api/business/events/{id}/tickets {ticket_types} GET /api/business/events/{id}/sales POST /api/business/tickets/scan {ticket_qr} POST /api/business/events/{id}/refund {booking_id} POST /api/business/events/{id}/announcement {message} | Business Service + Events Service | event_organizers | organizer_id, name, email, phone, verified, rating, events_count | 5 | 8 | 2.5 | 15.5 | Complexe | Event creation wizard, ticket inventory management, QR scanner web app, sales analytics, email blast system, refund processing, Stripe Connect pour payouts
PAYMENT | Payment Processing | MVP | Système | Traitement paiements intégré | Aucun bouton UI dédié (intégré flows booking) Méthodes: Card, Apple Pay, Google Pay, Cash (pay at venue) | Booking flow → Payment step → Sélection méthode → Stripe/Mollie SDK → 3DS authentication → Confirmation → Webhook processing Fallback: Pay at venue (no online payment) | POST /api/payments/create-intent {amount, currency, booking_id} POST /api/payments/confirm {payment_intent_id} POST /api/payments/webhook (Stripe webhook) GET /api/payments/{id}/status POST /api/payments/refund {payment_id, amount} | Payment Service | payments | payment_id, booking_id, user_id, amount, currency, method, status, stripe_payment_intent_id, refunded_amount, created_at | 3 | 8 | 2 | 13 | Complexe | Stripe/Mollie integration, PCI compliance (no card storage), 3DS2, webhook signature validation, idempotency, retry logic, refund handling, payment reconciliation
| Commission Management | MVP | Fonctionnalité cachée | Gestion commissions LYFE | Aucune UI utilisateur final Dashboard business: Voir commissions prélevées | Paiement booking/ticket → Commission LYFE calculée (X%) → Split payment Stripe Connect → Transfer vers restaurant/organizer (net) → LYFE reçoit commission Calcul: Commission = montant × taux (10-20% selon tier restaurant) | POST /api/payments/split {payment_id, venue_id} Stripe Connect: Transfer to connected account GET /api/business/payouts?venue_id= Internal: Accounting reconciliation queries | Payment Service | payment_commissions | commission_id, payment_id, venue_id, gross_amount, commission_rate, commission_amount, net_amount, transfer_id, status | 0 | 6 | 1.5 | 7.5 | Moyen | Stripe Connect setup, KYC verification restaurants, payout scheduling (weekly/monthly), commission rate tiers, accounting exports, tax handling
ANALYTICS | User Behavior Tracking | Beta | Système | Tracking comportemental exhaustif | Aucune UI visible Settings: Opt-out dans consentements | Tous événements app → Event tracking → Analytics pipeline → Data warehouse Événements: Screen views, button clicks, scroll depth, search queries, filters used, time spent, session duration, funnel drop-offs | POST /api/analytics/events {event_type, event_data, user_id, session_id, timestamp, device_info, location} Batch: POST /api/analytics/events/batch Internal: Queries sur data warehouse | Analytics Service | analytics_events | event_id, user_id, session_id, event_type, event_data_json, location, device_info, timestamp | 1 | 4 | 1.5 | 6.5 | Moyen | Amplitude/Mixpanel SDK, event batching, data warehouse (BigQuery/Redshift), GDPR compliance (anonymization), user consent checking, ML features extraction
| Business Intelligence | MVP | Système | Analytics pour business decisions | Dashboard admin interne KPIs: DAU, MAU, retention, revenue, conversion rates Cohort analysis Funnel analysis Geo heatmaps Popular cuisines/locations Peak booking times | Internal dashboards Data science team queries Automated reports | Internal BI tools queries GET /api/internal/analytics/kpis?period=30d GET /api/internal/analytics/cohorts GET /api/internal/analytics/funnels GET /api/internal/analytics/geo-heatmap ML: Churn prediction, recommendation models | Analytics Service | aggregated_analytics | Precomputed metrics tables, ML feature stores | 0 | 10 | 3 | 13 | Complexe | Data pipeline (Airflow/Luigi), BI dashboards (Metabase/Looker), ML models (Python/scikit-learn), A/B testing framework, data monetization prep (anonymized datasets)
AI_AGENT | LYFE Agent Basic | MVP | Fonctionnalité | Recommandations IA conversationnelles | Chat interface Poser question ('Où dîner ce soir?') Voir suggestions Affiner préférences Réserver depuis agent | Feed/Search → AI button → Chat modal → Query → AI response avec venues → Tap venue → Détail → Book Analytics: Queries, suggestions accepted, conversion rate | POST /api/ai/chat {message, user_id, context} Response: {reply, suggested_venues, confidence} Uses: OpenAI GPT-4 + vector search embeddings POST /api/ai/feedback {chat_id, accepted_suggestions} | AI Service | ai_chat_logs | chat_id, user_id, message, response, suggested_venue_ids, accepted, created_at | 2.5 | 6 | 1.5 | 10 | Complexe | OpenAI API integration, rate limiting, context management (last 5 messages), vector embeddings (Pinecone/Weaviate) for semantic venue search, prompt engineering, safety filters
| LYFE Agent Premium | MVP | Fonctionnalité | Agent IA avancé avec personnalisation | Toutes features Basic + Personnalisation profonde (apprendre préférences) Itinéraires multi-venues Recommandations groupe Booking automatique Voice input Image recognition ('Trouve restaurants similaires à cette photo') | Premium subscription required Plus de contexte historique Proactive suggestions ('Vous aimez X, essayez Y') | Same endpoints + premium features flag POST /api/ai/chat-premium {message, user_id, full_context} POST /api/ai/analyze-image {image} POST /api/ai/group-recommendations {user_ids, preferences} POST /api/ai/auto-book {venue_id, preferences} | AI Service | ai_premium_users | user_id, premium_tier, context_limit, auto_book_enabled | 3.5 | 8 | 2 | 13.5 | Complexe | GPT-4 Turbo, longer context window, DALL-E/Vision API for image analysis, collaborative filtering + content-based recommendations hybrid, auto-booking with user confirmation, voice transcription (Whisper API)
MEDIA | Image Upload & CDN | Beta | Système | Gestion médias utilisateurs | Upload photos profil, posts, reviews Compression automatique Modération contenu | User action upload → Validation (format, taille) → Compression client → Upload S3/CloudFlare → CDN URL → Display Moderation queue: AI flagging → Human review si needed | POST /api/media/upload {file, type} Response: {media_id, url, thumbnail_url} GET /api/media/{id} DELETE /api/media/{id} POST /api/media/moderate {media_id, action} | Media Service | media | media_id, user_id, url, thumbnail_url, type, size, moderation_status, created_at | 0 | 1 | 0.5 | 1.5 | Simple | S3/CloudFlare R2 storage, image compression (Sharp/Pillow), thumbnail generation, CDN (CloudFlare), moderation AI (AWS Rekognition), NSFW detection, virus scanning
| Video Processing | MVP | Système | Traitement vidéos stories/posts | Upload vidéo (stories, posts) Compression automatique Streaming optimisé | User upload video → Compression → Transcoding (multiple resolutions) → Upload → HLS/DASH streaming → Display Max: 60sec stories, 2min posts | POST /api/media/upload-video {file} Response: {video_id, hls_url, thumbnail_url, duration} Processing: Async job queue | Media Service | media | media_id, video_url, hls_url, duration, processing_status | 2.5 | 1.5 | 1 | 5 | Moyen | FFmpeg transcoding, multiple resolutions (360p/720p/1080p), HLS streaming, async processing (Celery), progress tracking, watermarking optional
MAPS | Map Integration | Beta | Composant | Intégration cartes interactives | Voir sur carte Obtenir itinéraire Voir venues sur carte (clustering) Filtrer carte par type venue | Détail venue → Map button → Carte centrée sur venue → Directions List view → Map toggle → Cluster markers → Tap marker → Venue preview → Détail | GET /api/venues/map?bounds=&type=&filters= Returns: {venues: [{id, name, location, type}]} Frontend: MapBox/Google Maps SDK | Venue Service | N/A (query sur venues) | location (PostGIS Point type) | 1.5 | 3 | 0.5 | 5 | Moyen | MapBox GL / Google Maps SDK, marker clustering, bounds-based query (PostGIS), directions deep link (Google Maps / Apple Maps), custom markers par type
MICROSERVICES | API Gateway | Beta | Infrastructure | Gateway centralisation APIs | N/A | N/A | / AWS API Gateway Routes: /api/auth/*, /api/venues/*, etc. → Backend services Rate limiting: 100 req/min per user Authentication: JWT validation Load balancing | API Gateway | N/A | N/A | 0 | 1 |  | 1 | Simple | Kong/Nginx, rate limiting (Redis), JWT validation middleware, CORS config, request logging, circuit breaker, health checks
| Auth Service | Beta | Service | Microservice authentification | N/A | N/A | FastAPI service Endpoints: /api/auth/* Database: PostgreSQL users, user_sessions Dependencies: Redis (session cache), Email service (verification) Scale: 2-4 instances behind load balancer | Auth Service | users | user_id, email, password_hash, phone, verified, created_at, last_login | 0 | 2 |  | 2 | Simple | FastAPI + SQLAlchemy, Argon2 hashing, JWT tokens (RS256), refresh tokens, Redis session cache, rate limiting, email verification (SendGrid/SES), OAuth2 flows
| Venue Service | Beta | Service | Microservice venues/restaurants/drinks | N/A | N/A | FastAPI service Endpoints: /api/venues/*, /api/restaurants/*, /api/drinks/* Database: PostgreSQL venues, drinks_venues Dependencies: Elasticsearch (search), Redis (cache) Scale: 3-6 instances (read-heavy) | Venue Service | restaurants | venue_id, name, cuisine, location (PostGIS), rating, price_level, photos, hours, capacity | 0 | 1.5 |  | 1.5 | Simple | FastAPI + SQLAlchemy, PostGIS extension, Elasticsearch sync (CDC or manual), Redis caching (TTL 5min), image URLs from CDN, pagination, filtering
| Events Service | Event | Service | Microservice événements & billets | N/A | N/A | FastAPI service Endpoints: /api/events/* Database: PostgreSQL events, event_tickets, ticket_inventory Dependencies: Payment Service, Notification Service Scale: 2-4 instances, Redis for inventory locking | Events Service | events | event_id, title, venue_id, date_time, capacity, tickets_available, price_range, organizer_id | 0 | 2 |  | 2 | Simple | FastAPI, race condition handling (Redis distributed locks), ticket inventory decrement (atomic transactions), webhook integrations, capacity monitoring alerts
| Booking Service | Beta | Service | Microservice réservations | N/A | N/A | FastAPI service Endpoints: /api/bookings/* Database: PostgreSQL bookings, booking_slots, venue_availability Dependencies: Venue Service, Payment Service, Loyalty Service, Notification Service Scale: 3-5 instances | Booking Service | bookings | booking_id, user_id, venue_id, date_time, guests, status, booking_reference, qr_code, points_earned | 0 | 2 |  | 2 | Simple | FastAPI, availability checking (Redis cache + PostgreSQL), QR code generation (qrcode lib), booking reference generation (unique), status state machine, notification triggers, transaction management
| Social Service | Beta | Service | Microservice fonctionnalités sociales | N/A | N/A | FastAPI service Endpoints: /api/feed/*, /api/posts/*, /api/stories/*, /api/users/*/follow, /api/community/* Database: PostgreSQL posts, post_likes, comments, stories, user_follows, leaderboard data Dependencies: User Service, Media Service, Notification Service Scale: 2-4 instances | Social Service | posts | post_id, user_id, venue_id, content, media_urls, likes_count, comments_count, created_at | 0 | 1.5 |  | 1.5 | Simple | FastAPI, feed ranking algorithm (engagement + recency), stories expiration (cron job), WebSocket for real-time updates, activity aggregation, graph queries (followers/following)
| Rating Service | Beta | Service | Microservice notations & reviews | N/A | N/A | FastAPI service Endpoints: /api/ratings/* Database: PostgreSQL venue_ratings, rating_comparables, rating_categories Dependencies: Booking Service (verify visit), Venue Service (update aggregates) Scale: 2-3 instances | Rating Service | venue_ratings | rating_id, user_id, venue_id, booking_id, final_score, sentiment, service_rating, food_rating, comment, helpful_count | 0 | 1.5 |  | 1.5 | Simple | FastAPI, scoring algorithm implementation, comparable venue selection (same cuisine + location), aggregate rating calculation (weighted average), spam detection, moderation queue integration
| Loyalty Service | Beta | Service | Microservice programme fidélité | N/A | N/A | FastAPI service Endpoints: /api/loyalty/* Database: PostgreSQL loyalty_accounts, loyalty_transactions, loyalty_rewards, loyalty_tiers Dependencies: Booking Service (award points), User Service Scale: 2-3 instances | Loyalty Service | loyalty_accounts | account_id, user_id, total_points, current_tier, tier_multiplier, expiring_points, tier_expiry_date | 0 | 1.5 |  | 1.5 | Simple | FastAPI, points calculation with tier multipliers, expiration logic (cron job), tier progression/demotion automation, reward redemption validation, transaction history, coupon generation
| Payment Service | MVP | Service | Microservice paiements | N/A | N/A | FastAPI service Endpoints: /api/payments/* Database: PostgreSQL payments, payment_commissions, refunds Dependencies: Stripe/Mollie SDK, Booking Service, Events Service Scale: 3-5 instances (critical, high availability) PCI compliant infrastructure | Payment Service | payments | payment_id, booking_id, amount, currency, method, status, stripe_payment_intent_id, commission_amount, created_at | 0 | 2 |  | 2 | Simple | FastAPI, Stripe/Mollie SDK, webhook handling (signature verification), idempotency keys, retry logic, refund processing, commission split (Stripe Connect), payment reconciliation, fraud detection, PCI DSS compliance
| Notification Service | Beta | Service | Microservice notifications | N/A | N/A | FastAPI service Endpoints: /api/notifications/* Database: PostgreSQL notifications, device_tokens Dependencies: Firebase Cloud Messaging, APNs, Email service (SendGrid), SMS service (Twilio) Scale: 2-4 instances, Message queue (RabbitMQ/SQS) Async processing | Notification Service | notifications | notification_id, user_id, type, title, body, deep_link, sent_at, delivered_at, opened_at | 0 | 2 |  | 2 | Simple | FastAPI, FCM/APNs integration, device token management, notification queue (Celery + Redis), retry logic, delivery tracking, unsubscribe management, notification templates, A/B testing framework, scheduled notifications
| Search Service | Beta | Service | Microservice recherche | N/A | N/A | FastAPI service Endpoints: /api/search/* Database: Elasticsearch (primary), PostgreSQL (metadata) Dependencies: Venue Service, Events Service, User Service Scale: 2-4 instances + Elasticsearch cluster (3 nodes) | Search Service | search_logs | search_id, user_id, query, filters_json, clicked_result_id, timestamp | 0 | 2 |  | 2 | Simple | FastAPI, Elasticsearch 8.x, full-text search, typo tolerance (fuzziness), synonyms config, multi-field search (name, cuisine, description), PostGIS integration for geo-search, autocomplete (edge ngrams), search analytics, ranking optimization (boost popular venues)
| Analytics Service | MVP | Service | Microservice analytics & BI | N/A | N/A | FastAPI service Endpoints: /api/analytics/* (internal), /api/internal/analytics/* Database: PostgreSQL (metadata), Data Warehouse (BigQuery/Redshift/ClickHouse) Dependencies: All services send events Scale: 2-3 instances + streaming pipeline Data pipeline: Kafka/Kinesis → Spark/Flink → Warehouse | Analytics Service | analytics_events | event_id, user_id, event_type, event_data_json, timestamp, session_id | 0 | 4 |  | 4 | Simple | FastAPI, event ingestion API, streaming pipeline (Kafka + Spark), data warehouse (BigQuery), BI dashboards (Metabase/Looker), ML models (churn, recommendations), GDPR anonymization, data monetization prep
| AI Service | MVP | Service | Microservice IA & ML | N/A | N/A | FastAPI service Endpoints: /api/ai/* Database: PostgreSQL (chat logs), Vector DB (Pinecone/Weaviate for embeddings) Dependencies: OpenAI API, Venue Service, User Service Scale: 2-4 instances, GPU instances for ML models Rate limiting & cost management | AI Service | ai_chat_logs | chat_id, user_id, message, response, suggested_venue_ids, created_at | 0 | 3 |  | 3 | Simple | FastAPI, OpenAI GPT-4 API, vector embeddings (text-embedding-ada-002), semantic search, prompt engineering, context management, safety filters (moderation API), recommendation models (collaborative + content-based), image analysis (GPT-4 Vision), rate limiting (cost control)
| Media Service | Beta | Service | Microservice gestion médias | N/A | N/A | FastAPI service Endpoints: /api/media/* Storage: S3/CloudFlare R2 Database: PostgreSQL media Dependencies: Moderation AI (AWS Rekognition), CDN (CloudFlare) Scale: 2-4 instances + async workers (Celery) for processing | Media Service | media | media_id, user_id, url, thumbnail_url, type, size_bytes, moderation_status, created_at | 0 | 1 |  | 1 | Simple | FastAPI, S3/R2 storage, image compression (Pillow), video transcoding (FFmpeg + Celery workers), thumbnail generation, CDN integration, moderation pipeline (AI + human review queue), virus scanning (ClamAV), NSFW detection
| Business Service | Beta | Service | Microservice dashboard restaurants/organizers | N/A | N/A | FastAPI service Endpoints: /api/business/* Database: PostgreSQL business_accounts, restaurant dashboard data Dependencies: Booking Service, Events Service, Payment Service, Analytics Service Scale: 1-2 instances (low traffic, B2B) Separate authentication (business accounts) | Business Service | business_accounts | business_id, venue_id, owner_id, subscription_tier, features_enabled, onboarded, created_at | 0 | 2 |  | 2 | Simple | FastAPI, separate auth for business users, dashboard analytics API, QR code validation, subscription management (Stripe Billing), webhook notifications new bookings, email reports, data exports (CSV/Excel)
INFRASTRUCTURE | PostgreSQL Database | Beta | Infrastructure | Base de données relationnelle principale | N/A | N/A | PostgreSQL 15+ Extensions: PostGIS (geo), pg_trgm (fuzzy search), uuid-ossp Replication: Primary + 2 read replicas Backups: Daily automated (Point-in-time recovery) Partitioning: Large tables (bookings, analytics_events) by date Connection pooling: PgBouncer | Multiple services | Multiple tables | Full schema design requis (50+ tables) | 0 | 0 | 15 | 15 | Complexe | AWS RDS PostgreSQL or self-managed, PostGIS for geo queries, read replicas for scaling, connection pooling, monitoring (pg_stat_statements), index optimization, partitioning strategy, backup/restore procedures, migration scripts (Alembic)
| Redis Cache | Beta | Infrastructure | Cache distribué & sessions | N/A | N/A | Redis 7+ Use cases: Session storage, API response cache, rate limiting, distributed locks (inventory), leaderboard (sorted sets), pub/sub (real-time events) Cluster: 3 nodes (master + 2 replicas) Persistence: AOF + RDS | Multiple services | N/A | N/A |  |  | 2 | 2 | Simple | AWS ElastiCache Redis or self-managed, cache invalidation strategies, TTL configuration, monitoring (memory usage, hit rate), eviction policies
| Elasticsearch | Beta | Infrastructure | Moteur recherche full-text | N/A | N/A | Elasticsearch 8+ Cluster: 3 nodes (master-eligible + data) Indices: venues, events, users Sync strategy: CDC (Change Data Capture) or manual indexing Backup: Snapshots daily | Search Service | Indices: venues | Mappings: text (analyzed), keyword, geo_point |  |  | 4 | 4 | Moyen | AWS OpenSearch or self-managed, index design, synonyms configuration, analyzers (language-specific), monitoring (cluster health, query performance), backup/restore
| Message Queue | Beta | Infrastructure | Queue asynchrone tâches | N/A | N/A | RabbitMQ or AWS SQS Queues: email_queue, push_notification_queue, media_processing_queue, analytics_events_queue Workers: Celery (Python) Retry logic: Dead letter queues | Multiple services | N/A | N/A |  |  | 2 | 2 | Simple | RabbitMQ/SQS, Celery workers (Python), retry policies, monitoring (queue length, processing time), dead letter queue handling
| CDN & Storage | Beta | Infrastructure | Stockage objets & CDN | N/A | N/A | Object Storage: AWS S3 or CloudFlare R2 CDN: CloudFlare (global distribution) Buckets: user-uploads, venue-images, media-processed Policies: Lifecycle (auto-delete old media), CORS, encryption at rest | Multiple services | N/A | N/A |  |  | 2 | 2 | Simple | S3/R2 setup, CloudFlare CDN integration, bucket policies, lifecycle rules, cost optimization (Intelligent Tiering), geo-distribution
| Monitoring & Logging | Beta | Infrastructure | Observabilité système | N/A | N/A | Logging: ELK Stack (Elasticsearch, Logstash, Kibana) or CloudWatch Logs Metrics: Prometheus + Grafana or DataDog APM: New Relic or DataDog APM Alerts: PagerDuty integration Distributed tracing: Jaeger or AWS X-Ray | All services | N/A | N/A |  |  | 3.5 | 3.5 | Simple | Centralized logging, metrics collection, dashboards (latency, errors, throughput), alerting rules, on-call rotation, distributed tracing for debugging microservices
| CI/CD Pipeline | Beta | Infrastructure | Déploiement continu | N/A | N/A | CI: GitHub Actions or GitLab CI CD: ArgoCD or Flux (GitOps) Containers: Docker + Kubernetes (EKS/GKE/AKS) Registry: ECR or Docker Hub Environments: Dev, Staging, Production Deployment strategy: Blue-green or Canary | All services | N/A | N/A |  |  | 10 | 10 | Complexe | Automated testing (unit, integration, e2e), Docker multi-stage builds, Kubernetes manifests, Helm charts, automated rollbacks, environment parity
| Security & Compliance | Beta | Infrastructure | Sécurité & conformité | N/A | N/A | WAF: CloudFlare or AWS WAF DDoS protection: CloudFlare SSL/TLS: Let's Encrypt auto-renewal Secrets management: AWS Secrets Manager or Vault Vulnerability scanning: Snyk or Trivy Compliance: GDPR, PCI-DSS (payment), SOC2 (future) Penetration testing: Annual | All services | N/A | N/A |  |  | 5 | 5 | Complexe | WAF rules, rate limiting, SSL configuration, secrets rotation, vulnerability scanning in CI, GDPR data handling, PCI compliance for payments, security audits
DATA_SEEDING | Initial Data Seed | MVP | Setup | Données initiales production | N/A | N/A | Seed data: Cities (Casablanca, Rabat, Marrakech, etc.), Categories (Moroccan, Italian, French, etc.), Amenities list, Loyalty tiers config Method: SQL scripts or Python seed scripts Run: Initial deployment only, then manual admin panel | Multiple services | Multiple tables | Cities, categories, amenities, tiers, default configs |  |  |  | 0 | Moyen | Seed scripts (SQL or Python), idempotent (can run multiple times), validation, backup before seeding
| Demo Data | MVP | Setup | Données de démonstration | N/A | N/A | Demo accounts: Test users (various tiers), Test restaurants/bars/events Purpose: Testing, demos, QA Method: Faker library (Python) for realistic data Environments: Dev, Staging (NOT production) Volume: 100 venues, 1000 users, 500 bookings, 2000 posts | Multiple services | All tables | Realistic names, addresses, photos (Lorem Picsum), dates |  |  |  | 0 | Moyen | Faker scripts, randomization, referential integrity, photo placeholders, reset script for clean state
ADMIN_INTERNAL | Internal Admin Panel | Beta | Écran (Internal) | Dashboard admin LYFE | Gérer utilisateurs: Voir, éditer, bannir, supprimer Gérer venues: Approve, reject, edit, feature (boost) Gérer événements: Moderate, approve, cancel Voir analytics: KPIs dashboard, revenue, user growth Modération contenu: Reviews, posts, media (approve/reject) Support tickets: Voir, répondre, escalader Gestion promotions: Créer codes promo, campagnes Logs & audit: User actions, admin actions, errors | Separate admin web app (React) Login admin → Dashboard → Sections management Role-based access: Super admin, moderator, support, analyst | GET /api/admin/users?search=&status= PUT /api/admin/users/{id}/ban GET /api/admin/venues?status=pending¦approved¦rejected PUT /api/admin/venues/{id}/approve GET /api/admin/analytics/dashboard GET /api/admin/moderation/queue POST /api/admin/promo-codes {code, discount, expiry} GET /api/admin/audit-logs | Admin Service | admin_users | admin_id, username, role, permissions, last_login, created_at | 8 | 12 | 3 | 23 | Complexe | React admin panel (React Admin or custom), role-based auth, action logs, search/filters, bulk actions, export CSV, audit trail
| Content Moderation | Beta | Fonctionnalité | Modération IA + humaine | Aucune UI utilisateur final Admin panel: Queue moderation | Upload media/post/review → AI scan (NSFW, hate speech) → Flagged si suspicious → Human review queue → Approve/Reject Auto-approved if AI confidence high | POST /api/moderation/scan {content_type, content_id} GET /api/admin/moderation/queue?type=image¦text PUT /api/moderation/{id}/approve PUT /api/moderation/{id}/reject {reason} | Moderation Service | moderation_queue | item_id, content_type, content_id, ai_score, flagged, reviewed, action, reviewer_id, timestamp |  | 5 | 1 | 6 | Complexe | AWS Rekognition (images), OpenAI Moderation API (text), moderation queue, review UI, action logs, appeals process
REVENUE_STREAMS | Restaurant Listings | Beta | Business Model | Listings restaurants payants | N/A (business decision) | N/A | Tiers: Free (basic listing), Premium ($50/month - featured, photos, priority), Enterprise ($200/month - analytics, ads, top ranking) Payment: Stripe Billing (subscriptions) Features: Premium badge, higher search ranking, promoted in feed | POST /api/business/subscribe {venue_id, tier} PUT /api/business/subscription/{id}/upgrade GET /api/business/subscription/{id} Webhook: Stripe subscription events | Business Service | business_subscriptions subscription_id, venue_id, tier, price, status, current_period_end, stripe_subscription_id |  | 2 | 0.5 | 2.5 | Simple | P3,Stripe Billing integration, subscription management, tier features enforcement, upgrade/downgrade flows, churn prevention
| Booking Commission | MVP | Business Model | Commission réservations | N/A (automatic) | N/A | Commission: 10-15% per booking (paid bookings only, not free reservations) Calculation: Booking amount × commission rate Split: Stripe Connect automatic transfer Settlement: Weekly to restaurant accounts Reporting: Monthly statements | Automatic via Payment Service GET /api/business/commissions?venue_id=&period= GET /api/business/statements/{month} | Payment Service | payment_commissions Already covered in Payment Service |  | 2 |  | 2 | Simple | P3,Already built in payment flow, reporting API, statement generation, dispute handling
| Event Ticketing Fee | Event | Business Model | Frais billetterie événements | N/A (automatic) | N/A | Fee: Fixed $2 + 5% per ticket sold Applied: At checkout (visible to user) Split: LYFE receives fee, organizer receives net Settlement: Weekly payouts to organizers Reporting: Real-time sales dashboard for organizers | Automatic via Payment Service GET /api/business/events/{id}/revenue | Payment Service | payment_commissions Already covered |  | 2 |  | 2 | Simple | P3,Fee calculation transparent, included in ticket price display, revenue reporting
| Advertising Platform | MVP | Business Model | Publicité in-app (future) | Banners sponsored dans feed Promoted venues dans search Stories ads | Future ads SDK integration Targeting: Location, interests, booking history Formats: Native ads, banner, interstitial Payment: CPM or CPC model | Future endpoints for ad serving Integration: Google AdMob or custom ad server | Ad Service | ad_campaigns | campaign_id, advertiser_id, budget, targeting, creative, clicks, impressions | 3 | 10.5 | 2.5 | 16 | Complexe | AdMob SDK or custom ad server, targeting engine, impression tracking, click tracking, ad creative management, advertiser dashboard
FEATURES_FUTUR | Influencer Program | MVP | Fonctionnalité (Future) | Programme influenceurs | Demande influenceur (form) Badges influenceur Commission affiliation | High-engagement users → Invite to influencer program → Perks (free bookings, commission referrals, verified badge) Requirements: >10k followers, >100 reviews, high engagement | POST /api/influencer/apply GET /api/influencer/dashboard {referrals, earnings} POST /api/influencer/referral-link {venue_id} | Influencer Service | influencer_accounts | influencer_id, user_id, tier, commission_rate, referrals_count, earnings, status |  | 3 | 1 | 4 | Moyen | Application review, referral tracking, commission calculation, payout processing, influencer analytics, content requirements
| Group Bookings | MVP | Fonctionnalité (Future) | Réservations groupes | Créer groupe Inviter membres Vote lieu/date Split payment | User creates group → Invites friends → Group votes on venue/date → Coordinator books → Payment split options Use case: Birthday parties, team dinners | POST /api/groups {name, members} POST /api/groups/{id}/poll {venues, dates} GET /api/groups/{id}/votes POST /api/bookings/group {group_id, venue_id, split_payment} | Group Service | booking_groups | group_id, organizer_id, members, poll_id, booking_id, created_at | 1.5 | 2 | 1 | 4.5 | Moyen | Group management, polling system, notifications, split payment (Stripe multiple destinations), group chat (optional)
| Waitlist Management | MVP | Fonctionnalité (Future) | Liste d'attente restaurants | Rejoindre waitlist (si complet) Notification quand disponible | Venue fully booked → Join waitlist option → User notified if cancellation → Book within 15min or offer expires For restaurants: Maximize occupancy, reduce no-shows | POST /api/bookings/{venue_id}/waitlist {date, time, guests} System: Monitor cancellations → Notify waitlist (FIFO) POST /api/bookings/waitlist/{id}/claim | Booking Service | booking_waitlist | waitlist_id, user_id, venue_id, date_time, guests, position, notified, claimed, expires_at | 0.5 | 2 | 1 | 3.5 | Moyen | Waitlist queue (Redis sorted set), cancellation listener, push notifications, expiration timer, claim endpoint
| Virtual Tours | MVP | Fonctionnalité (Future) | Visites virtuelles 360° | Voir visite virtuelle 360° Navigation intérieure restaurant | Venue detail → Virtual tour button → 360° viewer (Matterport embed or custom) For venues: Premium feature, attract customers For users: Preview ambiance before booking | GET /api/venues/{id}/virtual-tour Response: {tour_url, provider: 'matterport'} Embed: iframe in venue detail | Venue Service | venue_virtual_tours | tour_id, venue_id, tour_url, provider, created_at | 1.5 | 2 | 0.3 | 3.8 | Moyen | Matterport embed, 360° viewer library, upload flow for venues, storage costs, premium feature gate
| Table Selection | MVP | Fonctionnalité (Future) | Sélection table interactive | Choisir table sur plan interactif Préférences: Fenêtre, terrasse, calme | Booking flow → Table selection step → Interactive floor plan → Select preferred table → Book For restaurants: Optimize seating, customer preference For users: Control experience | GET /api/venues/{id}/floor-plan POST /api/bookings {venue_id, table_id, ...} PUT /api/business/venues/{id}/floor-plan {table_layout} | Booking Service | venue_tables | table_id, venue_id, table_number, seats, location_x, location_y, attributes, available | 3 | 2 | 1.5 | 6.5 | Moyen | Floor plan editor (business app), interactive SVG renderer, table availability real-time, collision detection, preference matching algorithm
| Dietary Filters Advanced | MVP | Fonctionnalité (Future) | Filtres alimentaires avancés | Filtrer: Vegan, Halal, Kosher, Gluten-free, etc. Sauvegarder préférences alimentaires Alert ingrédients | Search/filters → Dietary filters → Venues matching criteria Profile → Dietary preferences → Saved → Auto-applied to searches Venue detail → Dish ingredients → Allergen alerts | GET /api/venues/restaurants?dietary=vegan,halal GET /api/restaurants/{id}/menu-items?dietary_filter= PUT /api/users/{id}/dietary-preferences {preferences} | Venue Service | restaurant_menu_items | item_id, venue_id, name, description, price, dietary_tags, allergens, ingredients | 1 | 2 | 1 | 4 | Moyen | Dietary taxonomy, menu item tagging (manual or AI extraction), user preferences, filter logic, allergen warnings
| Live Occupancy | MVP | Fonctionnalité (Future) | Occupation en temps réel | Badge: Quiet / Moderate / Busy Historique patterns occupation | Venue detail → Live occupancy badge Based on: Current bookings, check-ins, historical data (ML model) For users: Avoid crowds or find busy spots For venues: Transparent capacity | GET /api/venues/{id}/occupancy Response: {level: 'quiet'¦'moderate'¦'busy', confidence, updated_at} ML: Predict occupancy based on time/day/season | Analytics Service | venue_occupancy_history | log_id, venue_id, timestamp, occupancy_level, bookings_count, checkins_count | 1 | 4 | 1 | 6 | Moyen | ML model (time-series prediction), real-time data aggregation, occupancy calculation, historical patterns, cache (Redis)
| Smart Recommendations | Beta | Fonctionnalité (Future) | Recommandations ML avancées | Section 'For You' personnalisée feed Notifications proactives suggestions | ML model: Collaborative filtering + content-based Features: User history, ratings, friends' activity, location, time, weather Output: Personalized venue recommendations Retrain: Weekly with new data | GET /api/recommendations?user_id= ML pipeline: Feature extraction → Model inference → Ranking A/B testing: Measure CTR, conversion vs baseline | AI Service | recommendation_model_features | user_id, feature_vector, last_updated | 0 | 12 | 3 | 15 | Complexe | ML model (scikit-learn, TensorFlow), feature engineering, model training pipeline, A/B testing framework, online serving (low latency)